## Sheet1
Week commencing | Consolidated report | Online tool | End of project conference | Evaluation
2018-12-24 | Questionnaire responses to Chris | Draft text | Agree date, speakers, invitees. Matt to book room and catering | Supporting material to Stephen (e.g. feedback forms
2018-12-31
2019-01-07
2019-01-14 |  |  | MF to write to participants and invitees
2019-01-21
2019-01-28 | Completion of final report
2019-02-04 |  | Completion and editing of video content |  | Skype call to discuss outcomes of workshops and views of participants
2019-02-11
2019-02-18
2019-02-25 |  |  | Final timetable and agenda agreed
2019-03-04 | Circulate to partners- agree final text | Circulate to social partners and groups
2019-03-11
2019-03-18
2019-03-25 | Circluation to social partners |  | Send out confirmations to attendees | Skype call on social partners' views on online tools
2019-04-01 |  | Roadshows with social partners
2019-04-08
2019-04-15 | Posting online and circulation to final conference participants |  | Circulate national report and online tool to invitees | Draft evaluation report
2019-04-22
2019-04-29 | Final conference
Formulas:
Week commencing = [Week commencing, row above]+7